IMPLEMENTATION PLAYBOOK

# ISIC 2019 Image Data Platform

A showcase-first Bronze-Silver-Gold implementation plan

| Field | Plan |
| --- | --- |
| Primary objective | Ingest, validate, version and publish the 25,331-image ISIC 2019 training set as reusable ML data products. |
| MVP finish line | Gold classifier manifest, one reproducible baseline, one workflow, fixture-based CI and a public case study. |
| Release 2 | Versioned super-resolution pairs and experiments, started only after the showcase MVP is published. |
| Reference stack | ADLS Gen2 + Python + Delta Silver tables + Parquet Gold manifest + Databricks Jobs/MLflow + local or third-party GPU. |
| Plan date | 2026-08-18 |

START HERE  Complete Phase 0 and Phase 1 first. Do not download the full image archive until the fixture pipeline and minimum storage permissions work. Treat every deferred production feature as optional until the public MVP is released.

# How to use this plan

- Move only a few task IDs into In Progress at once. Finish acceptance evidence before moving a task to Done.

- Tasks are ordered by dependency. A phase gate is a stop/go checkpoint, not optional documentation.

- The MVP cut line is the end of Phase 7. Super-resolution is a separate Release 2 backlog.

- When a design decision changes, update an architecture decision record and the affected dataset version; do not silently mutate published data.

# 1. Project outcome and boundaries

PROJECT OUTCOME  A reviewer can trace a model run back to an immutable Gold manifest, a validated Silver inventory and the exact Bronze image checksums used to create it.

## Success criteria

- A rerun of the Bronze backfill overwrites no verified source object.

- Every image is reconciled to a label and has an accepted or rejected state.

- Train/validation/test splits keep patient, lesion and duplicate groups together where identifiers permit.

- Gold manifests are immutable, checksummed and tied to source, processing and Git versions.

- Training uses a local SSD cache and logs dataset lineage to MLflow.

- CI proves behaviour with fixtures and never downloads the full ISIC dataset.

- The project is described as research/education, not as a clinical diagnostic system.

## MVP versus extension

| MVP - finish before expanding | Extension - begin only after MVP release |
| --- | --- |
| Bronze source preservation, checksums and idempotency | Super-resolution eligibility, pair construction and shards |
| Silver validation, normalized metadata and exact duplicates | Optional preprocessing experiments after the baseline |
| Grouped Gold classifier split and immutable manifest | Perceptual near-duplicate review, if exact hashes are insufficient |
| One transfer-learning baseline with MLflow lineage | Incremental ingestion from newer ISIC collections |
| One workflow, fixture CI, run summary and public case study | Multi-environment CI/CD, advanced monitoring and managed alerts |

# 2. Target data architecture

ISIC source  ->  Bronze originals  ->  Silver validated inventory  ->  Gold model-ready manifests  ->  local/GPU training  ->  MLflow

| Layer | Purpose | Physical assets | Must not happen |
| --- | --- | --- | --- |
| Bronze | Preserve source faithfully | Original JPEGs, CSV/JSON metadata, source manifest, ingestion ledger | Resize, recompress or overwrite source images |
| Silver | Validate and normalize | Delta inventory, labels, group IDs, quality and rejected records | Copy every JPEG merely to claim another layer |
| Gold | Publish for a specific consumer | Classifier manifest, preprocessing config, SR pair manifest/shards, dataset card | Change a published version in place |

## Preprocessing placement

| Transformation | Recommended placement | Reason |
| --- | --- | --- |
| Decode and dimension checks | Silver | Consumer-independent quality validation |
| Metadata and label normalization | Silver | Creates a trustworthy canonical schema |
| Resize, crop and augmentation | Gold config / runtime | Model- and experiment-specific |
| ImageNet mean/std | Training and inference runtime | Produces model-specific floating-point tensors; storing them wastes space |
| SR degradation and patches | Gold SR product | Consumer-specific derived pairs |

# 3. Initial Kanban board

WORK-IN-PROGRESS LIMIT  Keep no more than two engineering tasks in progress. Documentation and review may run alongside one engineering task.

| NOW | NEXT | LATER |
| --- | --- | --- |
| SCP-001 Repository, scope and fixtures | FND-001 Storage and configuration | BRZ-001 onward after the foundation gate |
| Goal: scope is locked and fixtures pass | Goal: the fixture pipeline can use storage | Release 2 stays blocked until the showcase release |

## Suggested cadence

| Timebox | Target outcome |
| --- | --- |
| Week 1 | Phase 0-1: scope, repository, fixtures, minimum storage and access |
| Week 2 | Phase 2: Bronze metadata, images and idempotency evidence |
| Week 3 | Phase 3: Silver inventory, quality gates and leakage groups |
| Week 4 | Phase 4: grouped splits, Gold manifest, preprocessing and cache |
| Week 5 | Phase 5-6: baseline, one workflow, fixture CI and run summary |
| Week 6 | Phase 7: case study, walkthrough, reproducibility review and MVP release |
| After release | Optional Release 2: super-resolution data product and experiment |

# Phase 0. Scope the showcase and create the fixture project

Phase goal: Lock a finishable classifier MVP and prove the project structure before using cloud resources.

PHASE GATE  A clean checkout runs the fixture pipeline locally and the README states the MVP, Release 2 and non-goals.

## Ordered tasks

### SCP-001  Create the repository, scope and fixture pipeline

Outcome: A coherent portfolio project that can prove behaviour without downloading ISIC data.

Depends on: None

Estimate: 0.5-1 day

- Define the MVP as Bronze ingestion, Silver validation, one Gold classifier manifest, one baseline model and a public case study.

- Create pyproject.toml, src/isic_pipeline, pipelines, tests, config, docs and notebooks directories.

- Add 10-20 synthetic or permitted fixtures covering valid, corrupt, duplicate and missing-label cases.

- List non-goals: clinical deployment, full-archive ingestion, real-time streaming, multi-environment CI/CD and super-resolution before Release 2.

Acceptance evidence

- A clean checkout installs and runs pytest.

- The fixture pipeline completes locally with no cloud credentials.

- README contains objective, MVP, Release 2 and non-goals.

# Phase 1. Create the minimum cloud foundation

Phase goal: Provision only the storage and configuration required by the showcase.

PHASE GATE  The fixture pipeline writes to ADLS, structured run metrics are visible and no credential is stored in Git.

## Ordered tasks

### FND-001  Provision storage and configure the pipeline

Outcome: One simple storage layout that works locally, in Databricks and from a training machine.

Depends on: SCP-001

Estimate: 0.5-1 day

- Create one ADLS Gen2 container with bronze, silver, gold and rejected prefixes.

- Use one pipeline identity or developer identity for ingestion; issue narrowly scoped read access to external GPU compute only when needed.

- Disable public blob access and configure one budget alert.

- Use Delta for Silver and operational tables, and publish the portable Gold training manifest as Parquet.

- Use environment-variable overrides and emit run_id, stage, counts, bytes, duration and status as structured logs.

Acceptance evidence

- The fixture pipeline writes Bronze and metadata outputs.

- Public access is disabled and no key or token is committed.

- One fixture run produces a unique run ID and stage metrics.

# Phase 2. Build the Bronze backfill

Phase goal: Acquire the fixed ISIC 2019 release efficiently and preserve original source bytes.

PHASE GATE  All expected records are accounted for and a second run performs zero unnecessary downloads or overwrites.

## Ordered tasks

### BRZ-001  Ingest official metadata and labels

Outcome: Immutable source metadata with checksums and an expected-image ledger.

Depends on: FND-001

Estimate: 0.5 day

- Download the official ISIC 2019 training metadata and ground truth before images.

- Record source URL, retrieval time, file size, SHA-256, source version, licence and attribution.

- Validate 25,331 unique labelled IDs across the expected eight training classes.

Acceptance evidence

- Metadata checksums remain stable across reruns.

- Unexpected labels, duplicate IDs and missing required columns fail the stage.

### BRZ-002  Ingest original images and prove idempotency

Outcome: Original JPEGs stored under stable image-ID paths with concise rerun evidence.

Depends on: BRZ-001

Estimate: 1-2 days

- Use the official challenge archive or isic-cli for the bulk historical load.

- Download to local or temporary landing storage, calculate SHA-256 and upload only missing or changed objects.

- Record downloaded, skipped, failed, bytes and duration; never resize or recompress Bronze images.

- Run the completed load a second time and capture its zero-change metrics.

Acceptance evidence

- Every expected ID is stored or has an explicit failure record.

- Every stored image has a checksum and source lineage.

- The second run reports zero unnecessary downloads and zero overwrites.

# Phase 3. Build the trustworthy Silver inventory

Phase goal: Validate and standardize the source without creating redundant image copies.

PHASE GATE  Every Bronze image has an accepted or rejected state and all Silver counts reconcile with the source ledger.

## Ordered tasks

### SLV-001  Build the validated image inventory

Outcome: One typed Silver record per source image plus simple quality evidence.

Depends on: BRZ-001, BRZ-002

Estimate: 1-1.5 days

- Decode each JPEG and record width, height, channels, format, file size, checksum and Bronze URI.

- Normalize image IDs, diagnosis codes and missing values while preserving original source values.

- Join labels to inventory and identify corrupt files, orphan labels and unlabelled images.

- Write rejected records with image ID, error code, message and source path; block Gold publication when reconciliation fails.

Acceptance evidence

- Inventory count reconciles with Bronze.

- No accepted image lacks a valid label.

- A deliberately corrupt fixture blocks publication and appears in rejected records.

### SLV-002  Create leakage-control groups

Outcome: Patient, lesion and exact-duplicate grouping fields for honest evaluation.

Depends on: SLV-001

Estimate: 0.5-1 day

- Group exact duplicates by SHA-256.

- Retain patient and lesion identifiers where supplied and report their completeness.

- Defer perceptual near-duplicate detection unless exact hashes and source identifiers prove insufficient.

Acceptance evidence

- Exact duplicate groups are materialized and reported.

- No grouping identifier is fabricated when the source does not provide one.

# Phase 4. Publish the Gold classifier product

Phase goal: Give training code one immutable contract instead of exposing pipeline internals.

PHASE GATE  A manifest checksum identifies the exact images, labels and grouped split assignment.

## Ordered tasks

### GLD-001  Generate grouped splits and publish the Gold manifest

Outcome: A deterministic, portable classifier dataset with source-to-model lineage.

Depends on: SLV-002

Estimate: 1 day

- Prioritize patient groups, then lesion groups, and always keep exact duplicates together.

- Stratify diagnosis distribution where grouping constraints permit.

- Publish image ID, Bronze URI, label, split, grouping fields and dataset version as Parquet.

- Record source version, Silver version, pipeline Git commit, class counts, exclusions and manifest SHA-256 in a concise dataset card.

Acceptance evidence

- No known group crosses splits.

- Two runs produce identical assignments and checksum.

- A clean environment can verify every referenced object.

### GLD-002  Version preprocessing and synchronize a local cache

Outcome: Fast training with reproducible runtime transforms and no per-epoch cloud streaming.

Depends on: GLD-001

Estimate: 0.5-1 day

- Version resize, aspect-ratio handling, augmentation and ImageNet mean/std as model runtime configuration.

- Do not persist resized images or normalized tensors unless measured training performance later justifies a disposable cache.

- Synchronize manifest images to local SSD and verify checksums before training.

Acceptance evidence

- A second cache sync downloads zero unchanged files.

- Training works offline after synchronization.

- Training and inference import the same deterministic preprocessing implementation.

# Phase 5. Prove the product with one classifier

Phase goal: Demonstrate Gold usability without turning the project into a broad model-search exercise.

PHASE GATE  One baseline experiment completes with dataset, preprocessing and Git lineage in MLflow.

## Ordered tasks

### ML-001  Validate locally and train one baseline

Outcome: One reproducible model result tied to exact data and code versions.

Depends on: GLD-002

Estimate: 1.5-2.5 days plus GPU time

- Run one local CPU smoke epoch on a small stratified subset before paid GPU use.

- Fine-tune one modest pretrained classifier such as ResNet-18.

- Report balanced accuracy, per-class recall, confusion matrix and a concise error analysis.

- Log dataset version, manifest checksum, Git commit, preprocessing version, parameters and artifacts to MLflow.

Acceptance evidence

- One command reproduces the smoke run from a clean checkout.

- MLflow links the baseline to one immutable Gold version.

- The report discusses class imbalance, grouping limitations and medical-use limitations.

# Phase 6. Add visible operational proof

Phase goal: Show production-minded behaviour without building an enterprise platform for a fixed dataset.

PHASE GATE  One workflow, one CI pipeline and one quality notebook provide the required operational evidence.

## Ordered tasks

### OPS-001  Add one orchestrated workflow and fixture-based CI

Outcome: A visible pipeline DAG plus fast automated evidence for the important contracts.

Depends on: BRZ-002, SLV-001, GLD-001

Estimate: 1 day

- Use one Databricks Job to call the tested CLI stages for metadata, image reconciliation, validation, quality gate and publication.

- Run formatting, linting, unit tests and the fixture pipeline in GitHub Actions.

- Cover corrupt image, missing label, idempotent rerun and deterministic split cases; never download the full dataset in CI.

- Do not create development, test and production deployment pipelines for the MVP.

Acceptance evidence

- A failed quality gate prevents Gold publication.

- A successful rerun skips unchanged Bronze images.

- CI passes without cloud secrets and displays a passing badge.

### OPS-002  Produce one quality and run-summary notebook

Outcome: A single reviewer-facing view of pipeline behaviour and dataset quality.

Depends on: OPS-001

Estimate: 0.5 day

- Show discovered, downloaded, skipped, rejected, bytes, duration and published version.

- Include image dimensions, diagnosis distribution, duplicate groups, split distribution and rejection reasons.

- Add a cache-hit summary if it is already available; do not build a separate dashboard.

Acceptance evidence

- The latest successful run is understandable from one notebook.

- Displayed counts reconcile across Bronze, Silver and Gold.

# Phase 7. Publish and verify the showcase

Phase goal: Make the work understandable without requiring access to Azure or Databricks.

PHASE GATE  A logged-out reviewer can understand the outcome, inspect evidence and reproduce the fixture pipeline.

## Ordered tasks

### SHOW-001  Publish and verify the portfolio case study

Outcome: A polished release that prioritizes evidence over additional infrastructure.

Depends on: ML-001, OPS-002

Estimate: 1 day

- Make the repository README the primary case study: problem, architecture, counts, idempotency, quality gates, grouped splits, caching, lineage and baseline results.

- Add architecture and quality screenshots; create a short walkthrough video only if it materially improves comprehension.

- Treat GitHub Pages as optional rather than a release dependency.

- Run the fixture pipeline from a clean checkout, verify public links while logged out, stop paid compute and tag the release.

Acceptance evidence

- The README communicates value before code navigation.

- All public links work while logged out and screenshots reveal no secrets.

- No paid compute remains running after demonstration.

# 8. Deferred work after the showcase release

DEFERRED MEANS DEFERRED  These items may improve a later release, but none should delay the classifier MVP or public case study.

## Release 2: super-resolution

| Order | Release 2 work item | Completion evidence |
| --- | --- | --- |
| 1 | Define minimum source resolution and reuse the grouped classifier split before extracting patches | No patient, lesion or duplicate group crosses SR splits |
| 2 | Version one deterministic x2/x4 degradation recipe | Pair ID reproduces the same LR/HR pixels from source ID, crop, seed and recipe |
| 3 | Publish a pair manifest and moderate-sized training shards | Shard checksums and member counts reconcile with the manifest |
| 4 | Run one modest SR baseline and inspect representative outputs | PSNR/SSIM, visual review and hallucination limitations are documented |
| 5 | Compare native-resize and SR-assisted classification | Both experiments use the same grouped source split and traceable dataset versions |

## Production details intentionally omitted from the MVP

- Separate development, test and production workspaces and deployment pipelines.

- Enterprise key rotation, elaborate identity topology and broad infrastructure-as-code coverage.

- Real-time ISIC notifications, streaming infrastructure and retraining triggers.

- Full monitoring and alerting stack with SLAs, paging and long-term operational support.

- Multiple orchestration systems, Kubernetes, feature stores or services not consumed by the project.

- Physical Silver copies of every JPEG or persisted ImageNet-normalized tensors.

# 9. Definition of Done

RULE  A task is not Done because code exists. It is Done when its acceptance evidence is visible and repeatable.

## Definition of Done for every task

- Code is committed and readable.

- Relevant unit or integration tests pass.

- Rerun behaviour is understood and safe.

- Documentation or configuration is updated when behaviour changes.

- Acceptance evidence is captured in the project board or README.

## MVP release checklist

| Area | Release condition |
| --- | --- |
| Data | Bronze count reconciles; Silver quality gate passes; Gold manifest is immutable and checksummed |
| Security | No secrets in Git; trainer is read-only; public blob access disabled |
| Cost | Budget alerts active; no GPU/cluster left running; disposable volumes reviewed |
| Reproducibility | Fixture pipeline runs from clean checkout; split and manifest are deterministic |
| ML | Baseline metrics and limitations published; MLflow run includes dataset and code lineage |
| Portfolio | README, architecture, quality evidence, screenshots/video and logged-out links verified |
| Ethics | Research-only disclaimer, licence attribution and medical limitations are visible |

## Key risks and controls

| Risk | Control |
| --- | --- |
| Scope expands into SR before the showcase works | Release 2 remains blocked until Phase 7 and the MVP release checklist are complete |
| Network access starves GPU training | Manifest-driven local SSD cache; synchronize once and verify checksums |
| Patient/lesion leakage inflates results | Group-aware splits and duplicate-group assertions |
| Preprocessing cannot be reproduced | Versioned config, shared train/inference package and deterministic tests |
| Derived images obscure source lineage | Immutable Bronze originals and parent/output checksums for every physical variant |
| Medical results are overstated | Research-only framing, calibration/error analysis and explicit limitations |
| Cloud cost surprises | Budget alerts, short GPU sessions, lifecycle rules and shutdown checklist |

## Authoritative project sources

ISIC challenge datasets: https://challenge.isic-archive.com/data/

ISIC 2019 challenge: https://challenge.isic-archive.com/landing/2019/

ISIC API bulk-download guidance: https://api.isic-archive.com/api/docs/swagger/

Official isic-cli: https://github.com/ImageMarkup/isic-cli

ISIC AWS Open Data listing: https://registry.opendata.aws/isic-archive/